## Issue List
Code Name: |  |  | Text Messenger |  |  |  |  | Error Color Code
High
Depracated
Issue List | [8 empty] | Potential Leak
No. | Date | Code | Module | Line No. | Issue Type | Issue | Resolution | Completed | Date Completed | Remarks
1 | 21.02.2014 |  | AddMessViewController.m | 77 | Memory | Potencial leak of an object stored into 'toLabel' | set [toLabel release]; | Done | 22.02.2014
2 | 21.02.2014 |  | MainController.m | 99 | Memory | Potencial leak of an object stored into 'selectedBackground' | in UIImageView *selectedBackground = [[[UIImageView alloc] initWithFrame:CGRectMake(0,0, 320,100)] autorelease] - inserted autorelease | Done | 22.02.2014
3 | 21.02.2014 |  | AddMessViewController.m | 161 | Memory | Potencial leak of an object stored into 'phone' | include autorelease | Done | 22.02.2014
4 | 21.02.2014 |  | AddMessViewController.m | 212 | Memory | Potencial leak of an object stored into 'formatter' | include autorelease | Done | 22.02.2014
5 | 21.02.2014 |  | AddMessViewController.m | 235 | Memory | Potencial leak of an object stored into 'pickerView'
6 | 21.02.2014 |  | JSTokenButton.m | 49 | Depracation | UILineBreakModeTailTruncation is depracated: first depracated in iOS6 | UILineBreakModeTailTruncation change to NSLineBreakByTruncatingTail | Done | 22.02.2014
7 | 21.02.2014 |  | ChatViewController.m | 15 | Semantic Issue | Incomplete Implementation
8 | 21.02.2014 |  | AddMessViewController.m | 139 | ARC Parse Issue | _bridge_transfer' casts have no effect when not using ARC | revise (__bridge_transfer NSString *) to (NSString) | Done | 22.02.2014
9 | 21.02.2014 |  | AddMessViewController.m | 140 | ARC Parse Issue | _bridge_transfer' casts have no effect when not using ARC | revise (__bridge_transfer NSString *) to (NSString) | Done | 22.02.2014
10 | 22.02.2014 |  | AddMessViewController.m | 98 | Semantic Issue | Incompatible pointer types assigning to 'UITextFied *' from 'NSMUtableArray *
11 | 23.03.2014 |  | AddMessViewController.m | 94 | NSInvalidArgument | Unrecognize selector sent to instance
12
13
14
15
16
17
18
19
20
^{ [_ccField setFrame:CGRectMake (0, [_toField frame].size.height + [_toField frame].origin.y, [_ccField frame].size.width, [_ccField frame].size.height)];

## Xcode Config
Project Name:
No. | Date | Module | Line No. | Issue | Resolution | Completed | Date Completed | Remarks
1 | 21.02.2014 | JSTokenButton.m JSTokenField.m |  | Automatic Referrence Counting | Change setting from "Build Settings" - Automatic referrence counting: OFF
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20

## Sheet4
| List of Modules Pending |  | Functionality Issue
1 | AutoComplete when user type for contact name | 1 | Do not allow return key / enter key in "Add contact field"
2 | TokenField | 2
3 | NSPopOver
4 | Autosearch
5